El Paso Water-Public Service Board

[If On-Call: NAME OF ON-CALL CONTRACT (MC#)]

[NAME OF PROJECT]

TASK ORDER NO. [#]

SCOPE OF SERVICES

CONSTRUCTION ADMINISTRATION AND RPR SERVICES

EXHIBIT A

SCOPE OF SERVICES

The ENGINEER shall provide the following Office Engineering and Field Construction Management Services for this project:

A.	OFFICE ENGINEERING SERVICES

Provide office engineering services to include consulting with and advising Owner on resolutions of problems due to actual field conditions encountered; and reviewing shop drawings and submittals from Contractor for compliance with design concepts.

1.	Provide the following field engineering support services:

a.	Conduct pre-construction conference; develop agenda; list of invitees; mail notices; and provide conference minutes.

b.	Make periodic visits to project site at intervals appropriate to various stages of construction to observe the quality of the executed work and report to Owner.

c.	Issue instructions from Owner to Contractor, through the RPR.

d.	Provide construction administration and supervise field engineering staff for the project.

e.	Coordinate with State, County, and City Agencies for construction in their jurisdictions.

f.	Review and approve shop drawings.

g.	Resolve design related construction problems.

h.	Provide monthly activities report whether invoice is sent or not.

i.	Make necessary interpretations and clarifications of Contract Documents.

j.	Prepare work directive changes (WDC) within 2 working days of change occurrence. Ensure issuance of approved WDC within 5 working days. WDCs shall include Engineer’s Estimate of Probable Cost, the probable impact to time (or lack thereof), and requires the signature of the Owner’s Project Administration Manager. Engineer shall subsequently negotiate the cost of each Work Directive Change and incorporate such changes to a proposed Change Order, with appropriate documentation attached, for Owner’s written acceptance.  Engineer is not authorized to commit to a final price or time extension without the written acceptance of the Owner in the form of a Change Order. A cost-price analysis shall be submitted with the proposed Change Order. When outside funding agencies are involved, they review and approve change orders for the following: Eligibility of funding; cost-price analysis; compliance with state design criteria; and environmental determination.  Additionally, change orders that exceed $100,000.00, or cumulative amount of change orders exceeding 25% of original contract price, or which constitute a departure from the original scope of work, require Public Service Board approval.

k.	Review and provide decisions as to suitability of work to RPR.

l.	Approve amounts of progress payments due to Contractor based on completion of work and recommend issuance of such payments by the Owner.  Transmit with Contractor's and Subcontractor's payrolls to Owner.

m.	Witness testing of facilities.

n.	Provide substantial completion inspection walk-through of the project with Contractor.

o.	Issue Engineer's Certificate of Substantial Completion timely. Include punch list items and all other closeout requirements. Submit to Owner for signature.  Contractor’s Retainage shall not be reduced below 5% without the written consent of the Owner. When outside funding agencies are involved, their approval of this reduction is required.

p.	Perform final inspection of project, recommend acceptance; and provide Engineer's Certificate of Final Completion, along with a complete closeout package, and submit to Owner’s Contracts office timely. An evaluation of Contractor's performance on the project shall be submitted as part of the closeout package. Using Contractor redlines, RPR daily logs, etc., as part of final closeout package, provide Owner with a mylar set of record drawings (3 mil) and on CADD diskette.

q.	When outside funding agencies are involved, a resolution by the PSB is required in order for a Certificate of Approval and Authorization of Release of Final payment to be issued.

2.	Conduct a warranty inspection of the project within 30 days before end of one year from the date of Substantial Completion and submit a written report to the Owner. Outside funding agencies may require a Certification of Project Performance.

B.	FIELD ENGINEERING AND INSPECTION SERVICES

- Provide a Full-time Resident Project Representative (RPR) to perform work in accordance with Suggested Listing of Duties, Responsibilities and Limitations of Authority of Resident Project Representative prepared by Engineer's Joint Contract Documents Committee, and superseded in amended form below:

a.	Review and approve the progress schedule updates and the schedule of Shop Drawing submittals prepared by Contractor.  Consult with Engineer concerning acceptability.

b.	Attend meetings with Contractor, such as progress meetings, job conferences and other project-related meetings, and prepare and circulate copies of minutes thereof.

c.	Serve as the liaison with Contractor, working principally through Contractor's superintendent.  Report to Engineer when clarifications and interpretations of the Contract Documents are needed and transmit to Contractor clarifications and interpretations as issued by Engineer.

d.	Serve as Owner's liaison with Contractor when Contractor's operation affects Owner's on-site operations.  Obtain from Owner additional details or information when required for proper execution of the work.

e.	Record date of receipt of Shop Drawing and samples of materials.  Submit to Office Engineer.

f.	Videotape the project corridor before start of construction and after completion to document pre- and post-project conditions.

g.	Advise Contractor he may not commence any Work requiring a Shop Drawing or sample if the submittal has not been approved.

h.	Conduct on-site observations of the Work in progress.  Advise the Engineer if the Work is, in general, proceeding in accordance with the Contract Documents.

i.	Notify the Engineer whenever Work is believed to be unsatisfactory, faulty, defective, not in conformance with the Contract Documents, damaged, or not meeting the requirements of any inspection, test or approval required to be made; and advise the Contractor of Work that Engineer believes should be corrected or rejected or should be uncovered for observation, or requires special testing, inspection, or approval.

j.	Verify that test, equipment and systems start-ups and operating and maintenance training are conducted in the presence of appropriate personnel, and the Contractor maintains adequate records thereof; and observe, record and report to the Engineer appropriate details relative to the test procedures and start-ups.

k.	Schedule field compliance tests and retests, confirm that these tests are conducted in the presence of the appropriate personnel; observe, record and report the appropriate test results.  Maintain records of failed tests.

l.	Accompany visiting inspectors representing public or other agencies having jurisdiction over the Project, and record the results of these inspections and report to Engineer.

m.	Ensure Wage Rates are posted on site.  Ensure all payrolls from prime and subcontractors are submitted with each monthly pay request as a condition precedent to approval and perform quality assurance reviews, as well as periodic interviews of various contractor employees on sire.  QA consists of performance of a representative number of checks of each prime and subcontractor payroll against the wage scale.  Highlight the employee rates checked before turning over reports with payrolls each month.  Ensure NPDES Permit and SW3P is posted at site and followed by Contractor.  Ensure Notice of Termination is included with the close-out package.

n.	Consider and evaluate Contractor's suggestions for modifications to drawings or specifications and transmit recommendations to Engineer.  Notify Contractor of the decision.

o.	Maintain for use at the job site orderly files for correspondence, reports of job conferences, Shop Drawings and Samples, Contract Documents including all Addenda, Work Directive Changes, Change Orders, Field Orders, additional Drawings issued subsequent to the execution of the Contract, clarifications and interpretations of the Contract Documents, progress reports, and other Project related documents.

p.	Keep a daily log recording Contractor's hours on the job site, weather conditions, equipment on site where applicable, data relative to questions about Work Directive Changes, Change Orders or changed conditions, list of job site visitors, daily activities, decisions, observations in general, and specific observations in more detail, as in the case of the observing test procedures.  Send copies to Engineer.

q.	Record names, addresses and telephone numbers of all Contractor, subcontractors and major suppliers of materials and equipment.

r.	Prepare monthly reports of progress of the Work and of Contractor's compliance with the progress schedule and schedule of Shop Drawings and sample submittals.  Submit reports with invoices and payrolls on a monthly basis.

s.	Notify Owner in advance of scheduled major tests, inspections, or start of important phases of the Work.  Coordinate with Owner’s operations staff.

t.	Obtain backup material from Contractor and prepare proposed Work Directive Changes, Change Orders, and Field Orders and forward to Office Engineer for negotiation.

u.	Notify Owner immediately upon the observation or notification of any accident.

v.	Review and recommend approval of payment requests by:

1.	Reviewing and approving the Contractor's estimate of the amount of work completed to date.

2.	Reviewing the Contractor's estimate of stored materials delivered to the job site but not incorporated in the Work completed to date.  Ensure invoice for materials is attached.

3.	Ensure receipt in next month's pay application of paid invoice for stored materials approved in previous month's application for payment.

4.	Ensure the Contractor and Subcontractor payrolls accompany each request.  Check for compliance with Wage Rate Schedule, perform periodic Employee Site Interviews using attached Record of Employee Interview form, Exhibit D.  Turn in to Owner bi-monthly.

w.	During the course of the Work, review certificates, maintenance and operation manuals and other data required to be assembled and furnished by the Contractor that are applicable to the items actually installed and are in accordance with the Contract Documents.  Forward this material to Office Engineer prior to issuance of Certificate of Substantial Completion to the Contractor.

x.	Recommend issuance of Certificate of Substantial Completion by Engineer.  Attach a list of observed items (punch list) requiring completion or correction.

y.	Attend final inspection in the company of Engineer, Owner, and Contractor and prepare a final list of items to be completed or corrected.

z.	Ensure that all items on final list have been completed or corrected and make recommendations to the Engineer to issue the Certificate of Final Completion for Owner's signature.

2.	Limitations of Authority.  Resident Project Representative:

a.	Shall not authorize any deviation from the Contract Documents or substitution of materials or equipment, unless authorized by Engineer.

b.	Shall not exceed limitations of Engineer's authority as set forth in the Agreement or the Contract Documents.

c.	Shall not undertake any of the responsibilities of Contractor, subcontractors or Contractor's superintendent.

d.	Shall not advise on, issue directions relative to or assume control over any aspect of the means, methods, techniques, sequences or procedures of construction unless such advice or directions are specifically required by the Contract Documents.

e.	Shall not advise on, issue directions regarding, or assume control over safety precautions and programs in connection with the Work.

f.	Shall not accept Shop Drawing or sample submittals from anyone other than Contractor.

g.	Shall not authorize Owner to occupy the Project in whole or in part.

h.	Shall not participate in specialized field or laboratory tests or inspections conducted by others except as specifically authorized by Engineer.

C.	SUBCONSULTANT SERVICES

**************************************************************************************

NOTE TO SPECIFIER:

Input Subconsultant name, function, and WBE Category.  Provide project specifics for each discipline 	required of the project.

Examples:	Geotechnical (indicate whether full testing service required or only for quality                assurance/quality control)

Surveying

Structural, Electrical, Mechanical, or Other

**************************************************************************************

NOTE TO SPECIFIER: Complete this section.

D.	OWNER's SERVICES

Example:	The Owner will provide all services associated with operation of water storage/transmission facilities, and construction crews to expose critical location of existing underground pipes and structures.

**************************************************************************************

E.	SPECIAL SERVICES

Shall be authorized in writing by Owner.  Basis of payment is to be determined at the time of authorization.  The following examples are not intended to be all-inclusive of types of special services which may be required.  The Engineer shall furnish or acquire for the Owner the following professional and technical services, when authorized.

1.	Make land surveys of real property for right-of-way and easement acquisitions and prepare plats and legal descriptions of same.

2.	Provide the necessary field parties, draftspersons, and other personnel for the setting of grades, lines, and limits of the Work, and to verify the accuracy of the Work as it is in progress.

3.	Provide detailed mill, shop, and/or laboratory inspection of materials and equipment when outside the El Paso metropolitan area.

4.	Assist Owner as an expert witness in any litigation arising from the development or construction of the Project.  This subsection shall not apply in the event the Engineer is a party to such litigation.

5.	Design Project additions, as may be necessary and not covered in the Engineer's Scope of Services.

6.	Conduct and/or coordinate specialty services such as traffic studies, photogrammetry, and environmental studies.

7.	Prepare applications and detailed support documentation for government grants and loans.

8.	Act on the Owner's behalf regarding subdivision plat review, zoning actions, and other land use matters.

9.	Prepare Operations and Maintenance (O & M) Manual.

10.	Conduct training and provide assistance in facilities operations.

11.	Review and evaluate the effects of design requirements prepared by other City offices and outside agencies which have been submitted to the Owner for incorporation into the project design.

12.	Prepare documents for alternate bids when not part of original Basic Services.

13.	Provide additional copies of reports, drawings and other documents.