| REQUIRED ITEMS FOR PROCESSING | INCLUDED |
| --- | --- |
| Page 1 of Change Order |  |
| - ENSURE THAT TOTAL AMOUNT OF CHANGE ORDER DOES NOT EXCEED 25% OF CONTRACT VALUE |  |
| - Check issuance date: (Date document prepared) Ensure it is current |  |
| - Check Change order number: Ensure the change order is numbered, is in sequential order, and if final it states final (Change Order 3-Final) |  |
| - Correct/complete name of Project and bid number |  |
| - Name of Contractor and short description of project |  |
| - YOU ARE DIRECTED TO MAKE THE FOLLOWING CHANGE TO THE CONTRACT DOCUMENTS: |  |
| - Descriptions of price change |  |
| b. Descriptions of changes to contract time indicating any milestones, substantial or final completion dates |  |
| c. Impact of this change order to Contract Price and Contract Time for each change order item |  |
| - PURPOSE OF CHANGE ORDER: Itemized list of items above |  |
| a. Description of what brought about the need for the Change Order |  |
| - ATTACHMENTS |  |
| a. Request from Contractor and/or owner |  |
| b. Related Correspondence |  |
| c. Related Work Change Directive(s) |  |
| d. Pricing submitted by Contractor |  |
| e. Memorandum of negotiations by Engineer |  |
| f. Applicable drawings and/or specifications |  |

CHANGE ORDER CHECK LIST

| Page 2 of Change Order | INCLUDED |
| --- | --- |
| - CHANGE IN CONTRACT PRICE: Original Price |  |
| a. This is the amount awarded to the Contractor |  |
| - CHANGE IN CONTRACT TIME: Original Contract Time |  |
| - Original number of calendar days allocated by the contract and due dates for substantial, final completions and any other milestones |  |
| - CONTRACT PRICE PRIOR TO THIS CHANGE ORDER: |  |
| - If there are any previously executed change orders that have changed the contract price. If not, the amount should be the original price. |  |
| - CONTRACT TIME PRIOR TO THIS CHANGE ORDER: |  |
| a. Number of calendar days allocated as changed by any previous change orders and revises current due date for each milestone |  |
| - NET INCREASE/DECREASE OF THIS CHANGE ORDER: Amount |  |
| - Specify either Net Increase or Net Decrease and amount (if no impact, strike out both) - Specify percent change to original price for this change order |  |
| - NET INCREASE/DECREASE OF THIS CHANGE ORDER: Time |  |
| - Input number of calendar days added to or subtracted from the specific milestone by this change order (if no impact, strike out both) |  |
| - CONTRACT PRICE WITH ALL APPROVED CHANGE ORDERS: |  |
| - Previous contract price plus change order totals to new contract price - Specify percent change to original price for all change orders |  |
| - CONTRACT TIME WITH ALL APPROVED CHANGE ORDERS: |  |
| - Total calendar days allocated and due dates for each milestone as revised by this change order |  |
| Page 3 of Change Order Engineer’s Cost Summary and Classification of source of change: | INCLUDED |
| - Liquidated Damages - Adjust Final Quantities - Unforeseen Conditions - Owner Ordered - Repay Owner - Errors - Omissions - Other - Specify |  |