## Risk Register
El Paso Water
[Fill In Project Name]
Prepared By: |  | [Project Manager Name]
Last Updated: |  | [MM/DD/YYYY]
Risk # | Threat / Opportunity | WBS # | Risk Event | Description of Impact | Risk Analysis (L/M/H Scale) |  |  | Type of Response | Risk Response Action and Status | Owner
[5 empty] | Probability (P) | Impact (I) | Risk Level
1
2
3
4
5
6
7
8
9
10
EXAMPLES
1 |  |  | Public Impact - Access to Property, Trash Pickup, Traffic, City Buses, Emergency Vehicle Access. |  |  |  |  | Mitigate
2 |  |  | Project requires coordination and release from Texas Historical Commission (THC). |  |  |  |  | Mitigate
3 |  |  | Project requires demolition. Need inspection for potential asbestos/lead and coordination with Texas Dept. of Health. |  |  |  |  | Mitigate
4 |  |  | The project becomes publicized, romanticized. | Client will be upset if publicizing leads to backlash from public, regulators, even higher up stakeholders in client org. | Low | Medium | Low | Mitigate | Register project as client confidential; instruct team of sensitivity; Also see risk # 2. No perceived need to keep separate, confidential files, however. | Ralph
5 |  |  | We do not report environmental or other permitting related concerns that we are legally or ethically required to do so. | Legal implications; impact on Native Am. Land. | Low | High | Medium | Avoid | Bring any such environ or regulatory concerns to the attention of client, and resolve the issue together. Factor in environ. concerns to comparative analyses of pipeline alignment, Scour analyses, etc. | Bill
6 |  |  | Interrupt potable water supply. | Population upset; fire protection jeopardized. | High | High | High | Mitigate | Need to maintain water supply uninterrupted to the extent possible; design alternatives should address. | Mary
7 |  |  | Construction costs not estimated, or inaccurate. | Client upset; doesn't like surprises. | High | High | High | Avoid | Plan and budget to prepare accurate const cost estimates; find competent resource(s) (e.g. J.G.). | Ralph
8 |  |  | Information we are given (written or verbal) may not be accurate. | We will make erroneous conclusions; may pick less optimum or more expensive solutions. | Medium | Medium | Medium | Mitigate | Team needs to clarify and confirm assumptions by cross checking assumptions with one another and multiple sources of information. | Sam
9 |  |  | Raw water source is hot (100+ deg F). | Certain materials may not be appropriate, from either structural or corrosive standpoint. | High | Medium | High | Accept | Conduct comparative analyses of mat'ls options, which also affect and are affected by placement( above or below ground, sleeved, etc), corrosiveness, and environmental impact. | Bill
10 |  |  | Environment is "corrosive". | Certain materials may not be appropriate, from a corrosive standpoint. | High | Medium | High | Accept | Conduct comparative analyses of mat'ls options, which also affect and are affected by placement( above or below ground, sleeved, etc), corrosiveness, and environmental impact. | Ralph
11 |  |  | Maintenance regimens may not be able to be counted on. | Shorter life of new infrastructure. | High | Medium | Medium | Transfer | First, this is a client issue; however we should offer to perform comparative analyses of life cycle costs, together with assessments of maintenance needs, probabilities of achieving same; and present options to client for "lock-in". | Client
12 |  |  | Deficient, existing infrastructure, relied upon (e.g. disinfection, electrical supply, Hot Rod tanks, existing piping to be retained either for transmission, or sleeve). | Overlooked deficiencies result in "solution" below acceptable standard, perhaps even unsafe. | Medium | Medium | Medium | Avoid | Adequately research soundness of any exiting systems to be relied upon (exclude/include? Existing WTP?). | Bill
13 |  |  | Insufficient attention paid to PM practices. | Client's hot buttons pushed (e.g. not kept up to date according to their expectations). Budget is wasted and undesired changes arise (tech, schedule, and financial come as surprises). | Medium | Low | Low | Avoid | Develop and implement a Project Management Plan, including detailed schedule/budget, communication mgmt plan, risk mgmt plan, subcontractor mgmt plan, CADD plan, and RAM. | Mary
14 |  |  | Work being done in four offices could lead to compromised communications and team diverging from "plan". | Project inefficiencies, rework, missed deadlines, busted budgets. | Medium | Medium | Medium | Mitigate | Mitigate by using communication management tools, including protocols for managing documents, establishing CADD standard, naming versions, keeping them as centrally located as possible, and holding progress, technical review meetings at least weekly, even if by teleconference - communicate risk and communication plans to entire team. | Mary
15 |  |  | Constructability and operability reviews get overlooked. | Design solution effectiveness compromised. | High | Medium | Medium | Avoid | Use the PSP design linear map guideline, and associated templates; ensure that the right resources are available internally, or if not, arrange for subbing out. | Mary
LOOK-UP LISTS
Probability & Risk Level
Very High
High
Medium
Low
Very Low
Type of Risk
Threat
Opportunity
Type of Response
Mitigate
Avoid
Transfer
Contingency
Enhance
Share
Accept
Other
NOTES
· Scroll down sheet for examples, which can help you visualize what is expected and useful from a risk management perspective.
· The Risk # column is for chronological reference, or any numbering system you choose.
· Under WBS #, enter what WBSs or Tasks are associated with the risk event (use “all” or "various" if the risk is applicable across the project).
· Enter the risk event to be "what might occur that is of concern".
· Probability, impact and risk level can be provided using a Low/ Medium High scale.
· Enter impact, probability and risk level as if risks were NOT going to be addressed based upon current experience (not wishful thinking!) and overall risk level from the point of view of IMPACT.
· Enter the recommended type of response (Mitigate, Avoid, Transfer, Accept or Other ) using the pull-down menu.
· Describe how the selected strategy (type of response) will be implemented and the status of the plan.
· Insert additional rows as needed.