## LD Justification
EL PASO WATER JUSTIFICATION FOR LIQUIDATED DAMAGES RATES - STORMWATER
[ENTER STORMWATER PROJECT NAME]
| BID NO.: | [16 empty] | SW##-##
LIQUIDATED DAMAGES RATES SUMMARY:
| MILESTONE: |  |  |  |  | DESCRIPTION: | [21 empty] | DURATION (DAYS)*: |  |  | DAILY RATE ROUNDED:
| No. 1 |  |  |  |  | [Enter Description from "Milestone 1 Justification" TAB, Otherwise enter Not Applicable] | [21 empty] | 0 |  |  | 3000
| No. 2 |  |  |  |  | Not Applicable | [21 empty] | 0 |  |  | 0
| No. 3 |  |  |  |  | Not Applicable | [21 empty] | 0 |  |  | 0
| No. 4 |  |  |  |  | Not Applicable | [21 empty] | 0 |  |  | 0
| Substantial |  |  |  |  | Substantial Completion | [21 empty] | 150 |  |  | 800
| Final |  |  |  |  | Final Completion | [21 empty] | 180 |  |  | 750
*CONTRACT TIME ESTABLISHED TO REACH THE CONTRACTUAL DEADLINES, TO BEGIN THE DAY THE NOTICE TO PROCEED AND/OR CLOCK START DATE IS ISSUED.
LIQUIDATED DAMAGES RATE CALCULATIONS:
| MILESTONE NO. 1: | [17 empty] | MILESTONE NO. 2:
| ITEM #: |  |  | DESCRIPTION (modify as needed): | [10 empty] | RATE |  |  |  | ITEM #: |  |  | DESCRIPTION (modify as needed): | [8 empty] | RATE
| 1 |  |  | DAILY EXTENDED RATE OF EPW COSTS (ops, prod., treatment, containment, etc) FOR FAILURE TO MEET MILESTONE | [10 empty] | 0 |  |  |  | 1 |  |  | DAILY EXTENDED RATE OF EPW COSTS (ops, prod., treatment, containment, etc) FOR FAILURE TO MEET MILESTONE | [8 empty] | 0
| 2 |  |  | DAILY RATE OF EXTENDED PROJECT COSTS FOR DESIGN ENGINEER**: | [10 empty] | 0 |  |  |  | 2 |  |  | DAILY RATE OF EXTENDED PROJECT COSTS FOR DESIGN ENGINEER**: | [8 empty] | 0
| 3 |  |  | OTHER ANCIALLARY COSTS #1 (i.e. RR Flagger Fees, Extended Dewatering, etc.): | [10 empty] | 3000 |  |  |  | 3 |  |  | OTHER ANCIALLARY COSTS #1 (i.e. RR Flagger Fees, Extended Dewatering, etc.): | [8 empty] | 0
| 4 |  |  | OTHER ANCIALLARY COSTS #2 (i.e. RR Flagger Fees, Extended Dewatering, etc.): | [10 empty] | 0 |  |  |  | 4 |  |  | OTHER ANCIALLARY COSTS #2 (i.e. RR Flagger Fees, Extended Dewatering, etc.): | [8 empty] | 0
| TOTAL LD RATE: | [13 empty] | 3000 |  |  |  | TOTAL LD RATE: | [11 empty] | 0
| MILESTONE NO. 3: | [17 empty] | MILESTONE NO. 4:
| ITEM #: |  |  | DESCRIPTION (modify as needed): | [10 empty] | RATE |  |  |  | ITEM #: |  |  | DESCRIPTION (modify as needed): | [8 empty] | RATE
| 1 |  |  | DAILY EXTENDED RATE OF EPW COSTS (ops, prod., treatment, containment, etc) FOR FAILURE TO MEET MILESTONE | [10 empty] | 0 |  |  |  | 1 |  |  | DAILY EXTENDED RATE OF EPW COSTS (ops, prod., treatment, containment, etc) FOR FAILURE TO MEET MILESTONE | [8 empty] | 0
| 2 |  |  | DAILY RATE OF EXTENDED PROJECT COSTS FOR DESIGN ENGINEER**: | [10 empty] | 0 |  |  |  | 2 |  |  | DAILY RATE OF EXTENDED PROJECT COSTS FOR DESIGN ENGINEER**: | [8 empty] | 0
| 3 |  |  | OTHER ANCIALLARY COSTS #1 (i.e. RR Flagger Fees, Extended Dewatering, etc.): | [10 empty] | 0 |  |  |  | 3 |  |  | OTHER ANCIALLARY COSTS #1 (i.e. RR Flagger Fees, Extended Dewatering, etc.): | [8 empty] | 0
| 4 |  |  | OTHER ANCIALLARY COSTS #2 (i.e. RR Flagger Fees, Extended Dewatering, etc.): | [10 empty] | 0 |  |  |  | 4 |  |  | OTHER ANCIALLARY COSTS #2 (i.e. RR Flagger Fees, Extended Dewatering, etc.): | [8 empty] | 0
| TOTAL LD RATE: | [13 empty] | 0 |  |  |  | TOTAL LD RATE: | [11 empty] | 0
| SUBSTANTIAL COMPLETION | [17 empty] | FINAL COMPLETION
[5 empty] | EPWATER SW TECH SERVICES | [6 empty] | EPW CONSTRUCTION ADMIN | [10 empty] | EPWATER SW TECH SERVICES |  |  |  | EPW CONSTRUCTION ADMIN
| Position: |  |  |  | EDM |  | PM | SEC |  | OH/O&M |  | EDM |  | INSP |  | OH/O&M |  |  | Position: |  |  |  | EDM | PM | SEC | OH/O&M | EDM |  |  | INSP |  | OH/O&M
| Rate: |  |  |  | 88.7524 |  | 46.5777 | 23.4897 |  | 183.1731 |  | 88.7524 |  | 55.5774 |  | 152.9808 |  |  | Rate: |  |  |  | 88.7524 | 46.5777 | 23.4897 | 183.1731 | 88.7524 |  |  | 55.5774 |  | 152.9808
| Daily Duration: |  |  |  | 0.1 |  | 1 | 0.1 |  | 1.2 |  | 0.1 |  | 1 |  | 1.1 |  |  | Daily Duration: |  |  |  | 0.1 | 1 | 0.1 | 1.2 | 0.1 |  |  | 1 |  | 1.1
| Sub-Total |  |  |  | 8.8752 |  | 46.5777 | 2.349 |  | 219.8077 |  | 8.8752 |  | 55.5774 |  | 168.2788 |  |  | Sub-Total |  |  |  | 8.8752 | 46.5777 | 2.349 | 219.8077 | 8.8752 |  |  | 55.5774 |  | 168.2788
| Daily Total: |  |  |  | 510.3411 | [13 empty] | Daily Total: |  |  |  | 510.3411
| EPWATER SUPPORT & CLERICAL @ XX% OF DAILY TOTAL RATE*: | [11 empty] | 35% |  | 178.6194 |  |  |  | EPWATER SUPPORT & CLERICAL @ XX% OF DAILY TOTAL RATE*: | [9 empty] | 35% |  | 178.6194
| DAILY RATE OF EXTENDED PROJECT COSTS FOR DESIGN ENGINEER**: | [13 empty] | 107.14 |  |  |  | DAILY RATE OF EXTENDED PROJECT COSTS FOR DESIGN ENGINEER**: | [11 empty] | 62.09
| OTHER ANCIALLARY COSTS #1 (i.e. RR Flagger Fees, Extended Dewatering, etc.): | [13 empty] | 0 |  |  |  | OTHER ANCIALLARY COSTS #1 (i.e. RR Flagger Fees, Extended Dewatering, etc.): | [11 empty] | 0
| OTHER ANCIALLARY COSTS #2 (i.e. RR Flagger Fees, Extended Dewatering, etc.): | [13 empty] | 0 |  |  |  | OTHER ANCIALLARY COSTS #2 (i.e. RR Flagger Fees, Extended Dewatering, etc.): | [11 empty] | 0
| TOTAL LD RATE: | [13 empty] | 796.1005 |  |  |  | TOTAL LD RATE: | [11 empty] | 751.0505
*TO INCLUDE, BUT NOT LIMITED TO, EXECUTIVE MANAGEMENT; OPERATIONS; ACCOUNTING; PURCHASING; LEGAL; CLERICAL; COMMUNICATIONS; ETC..
**DESIGN ENGINEER TO SUBMIT BREAKDOWN FOR JUSTIFICATION OF EXTENDED PROJECT COSTS DUE TO EXTENDED DURATION
| EDM = ENGINEERING DIVISION MANAGER | [7 empty] | PM= PROJECT MANAGER | [7 empty] | SEC = SENIOR SECRETARY | [7 empty] | INSP = INSPECTOR
|  |  | EPW = EL PASO WATER | [7 empty] | LD = LIQUIDATED DAMAGES | [9 empty] | OH/O&M = OVERHEAD AND OPERATION AND MAINTENANCE
|  | PROJECT MANAGER: | [17 empty] | DATE:

## EPW Rate Determination
*Per COEP 2012 Professional/Managerial Pay Schedule. Max Pay Rate used to account for inflation and for convenience
**Assume 35% to account for inflation and for convenience |  |  | Loaded OH Rate: |  | 35%
SECTION 220 STORMWATER TECHNICAL SERVICES
Salaries & Wages | [5 empty] | 2019-20 OH and O&M
Position | Pay Grade | # of Positions | Maximum Pay Rate HRLY* | Average HRLY Rate | Loaded Pay Rate** |  | Materials and Supplies | Maintenance (Communication Equipment) | Miscellaneous
Engineering Division Manager | EX4 | 1 | 65.7425 | 65.7425 | 88.7524 | FY Budget | 19000 | 10900 | 351100
Utility Engineer | PM132 | 3 | 40.9229 | 34.502 | 46.5777
Utility Engineer Associate | PM128 | 0 | 33.2092
Engineering Associate | PM126 | 2 | 30.1218 |  |  | Conversion to HOURLY Costs | 9.1346 | 5.2404 | 168.7981
Engineering Lead Technician | GS56 | 2 | 29.2509
Engineering Senior Technician | GS46 | 0 | 26.5314
[6 empty] | Sum Total Hourly Costs | 183.1731
Secretary | GS46 | 1 | 17.3998 | 17.3998 | 23.4897
*Per COEP 2012 Professional/Managerial Pay Schedule. Max Pay Rate used to account for inflation and for convenience
**Assume 35% to account for inflation and for convenience |  |  | Loaded OH Rate: |  | 35%
SECTION 325 ENGINEERING PROJECT MANAGEMENT
Salaries & Wages | [5 empty] | 2019-20 OH and O&M
Position | Pay Grade | # of Positions | Maximum Pay Rate HRLY* | Average HRLY Rate | Loaded Pay Rate** |  | Materials and Supplies | Maintenance (Communication Equipment) | Miscellaneous
Engineering Division Manager | EX4 | 1 | 65.7425 | 65.7425 | 88.7524 | FY Budget | 9100 | 6100 | 106800
Utility Engineer | PM132 | 2 | 40.9229 | 36.1893 | 48.8556
Civil Engineer | PM132 | 2 | 40.9229
Engineering Program Administrator | PM129 | 1 | 35.3506 |  |  | Conversion to HOURLY Costs | 4.375 | 2.9327 | 51.3462
Utility Engineer Associate | PM128 | 2 | 33.2092
Civil Engineer Associate | PM128 | 0 | 33.2092
Capital Improvement Project Associate | PM126 | 2 | 30.1217 |  |  | Sum Total Hourly Costs | 58.6538
Senior Secretary | GS49 | 1 | 20.4721 | 20.4721 | 27.6374
*Per COEP 2012 Professional/Managerial Pay Schedule. Max Pay Rate used to account for inflation and for convenience
**Assume 35% to account for inflation and for convenience |  |  | Loaded OH Rate: |  | 35%
SECTION 335 CONSTRUCTION PROJECT MANAGEMENT
Salaries & Wages | [5 empty] | 2019-20 OH and O&M
Position | Pay Grade | # of Positions | Maximum Pay Rate HRLY* | Average HRLY Rate | Loaded Pay Rate** |  | Materials and Supplies | Maintenance (Communication Equipment) | Miscellaneous
Engineering Division Manager | EX4 | 1 | 65.7425 | 65.7425 | 88.7524 | FY Budget | 6900 | 10220 | 301080
Construction Superintendent | PM134 | 3 | 46.1294 | 41.1685 | 55.5774
Utility Engineer | PM132 | 1 | 40.9229
Utility Engineer Associate | PM128 | 0 | 33.2092 |  |  | Conversion to HOURLY Costs | 3.3173 | 4.9135 | 144.75
Engineering Lead Technician | GS56 | 0 | 29.2509
Engineering Senior Technician | GS54 | 1 | 26.5314
Water Services Inspector | GS50 | 0 | 21.4958 |  |  | Sum Total Hourly Costs | 152.9808
Construction Inspector | GS48 | 0 | 19.4973

## Milestone 1 Justification
MILESTONE NO. 1:
ITEM #: | DESCRIPTION [Example: Completion of all work from Station 14+18 to Station 24+45] | RATE
1 | DAILY EXTENDED RATE OF EPW COSTS (ops, prod., treatment, containment, etc) FOR FAILURE TO MEET MILESTONE | 0
JUSTIFICATION FOR ITEM RATE:
[Example: None.]
2 | DAILY RATE OF EXTENDED PROJECT COSTS FOR DESIGN ENGINEER**: | 0
JUSTIFICATION FOR ITEM RATE:
[Example: None.]
3 | OTHER ANCIALLARY COSTS #1 (i.e. RR Flagger Fees, Extended Dewatering, etc.): | 3000
JUSTIFICATION FOR ITEM RATE:
[Example: Costs for extended BNSF Railroad Flagging and Inspection estimated @ $3000.00 per day]
4 | OTHER ANCIALLARY COSTS #2 (i.e. RR Flagger Fees, Extended Dewatering, etc.): | 0
JUSTIFICATION FOR ITEM RATE:
[Example: None.]
TOTAL LD RATE: |  | 3000

## Milestone 2 Justification
MILESTONE NO. 2:
ITEM #: | DESCRIPTION | RATE
1 | DAILY EXTENDED RATE OF EPW COSTS (ops, prod., treatment, containment, etc) FOR FAILURE TO MEET MILESTONE | 0
JUSTIFICATION FOR ITEM RATE:
[Enter Justification]
2 | DAILY RATE OF EXTENDED PROJECT COSTS FOR DESIGN ENGINEER**: | 0
JUSTIFICATION FOR ITEM RATE:
[Enter Justification]
3 | OTHER ANCIALLARY COSTS #1 (i.e. RR Flagger Fees, Extended Dewatering, etc.): | 0
JUSTIFICATION FOR ITEM RATE:
[Enter Justification]
4 | OTHER ANCIALLARY COSTS #2 (i.e. RR Flagger Fees, Extended Dewatering, etc.): | 0
JUSTIFICATION FOR ITEM RATE:
[Enter Justification]
TOTAL LD RATE: |  | 0

## Milestone 3 Justification
MILESTONE NO. 3:
ITEM #: | DESCRIPTION | RATE
1 | DAILY EXTENDED RATE OF EPW COSTS (ops, prod., treatment, containment, etc) FOR FAILURE TO MEET MILESTONE | 0
JUSTIFICATION FOR ITEM RATE:
[Enter Justification]
2 | DAILY RATE OF EXTENDED PROJECT COSTS FOR DESIGN ENGINEER**: | 0
JUSTIFICATION FOR ITEM RATE:
[Enter Justification]
3 | OTHER ANCIALLARY COSTS #1 (i.e. RR Flagger Fees, Extended Dewatering, etc.): | 0
JUSTIFICATION FOR ITEM RATE:
[Enter Justification]
4 | OTHER ANCIALLARY COSTS #2 (i.e. RR Flagger Fees, Extended Dewatering, etc.): | 0
JUSTIFICATION FOR ITEM RATE:
[Enter Justification]
TOTAL LD RATE: |  | 0

## Milestone 4 Justification
MILESTONE NO. 4:
ITEM #: | DESCRIPTION | RATE
1 | DAILY EXTENDED RATE OF EPW COSTS (ops, prod., treatment, containment, etc) FOR FAILURE TO MEET MILESTONE | 0
JUSTIFICATION FOR ITEM RATE:
[Enter Justification]
2 | DAILY RATE OF EXTENDED PROJECT COSTS FOR DESIGN ENGINEER**: | 0
JUSTIFICATION FOR ITEM RATE:
[Enter Justification]
3 | OTHER ANCIALLARY COSTS #1 (i.e. RR Flagger Fees, Extended Dewatering, etc.): | 0
JUSTIFICATION FOR ITEM RATE:
[Enter Justification]
4 | OTHER ANCIALLARY COSTS #2 (i.e. RR Flagger Fees, Extended Dewatering, etc.): | 0
JUSTIFICATION FOR ITEM RATE:
[Enter Justification]
TOTAL LD RATE: |  | 0